## Dashboard
Anti-Scam — Weekly Task Tracker 2026–2027
KPI | Giá trị | Owner | WP | Done | Progress
Tổng Work Package | 75 | Hùng | 19 | 0 | 0%
Core WP | 67 | Khải | 17 | 0 | 0%
Future WP | 8 | Kiên | 19 | 0 | 0%
MVP release | 2026-10-30 | Thắng | 20 | 0 | 0%
Public Beta | 2027-01-22 | Tổng | 75 | 0 | 0%
Quy tắc: tick ☑ chỉ khi có evidence (PR/test/demo/doc). Future WP là optional và không được kéo dependency ngược vào core.

## Release Roadmap
Version/Mốc | Ngày | Loại | Mục tiêu / Scope | Gate
v0.1.0 | 2026-10-30 | MVP | Vertical slice ổn định: auth/session, text scan, URL scan + SSRF, risk result/history, orchestration nền tảng. | Release
v0.2.0 | 2026-11-20 | Core Expansion 1 | Entity reputation + threat/reputation nền tảng + community report cơ bản. | Release
v0.3.0 | 2026-12-11 | Core Expansion 2 | Moderation, notification nền tảng, QR baseline, rule/threat management mở rộng. | Release
v0.4.0 | 2027-01-08 | Beta Candidate | AI async baseline, export/ops hardening, Google OIDC/profile/security polish. | Release
v0.5.0-beta.1 | 2027-01-22 | Public Beta | Mở beta cho user trải nghiệm; bật feedback/data collection và monitoring. | Release
v0.5.0-beta.2 | 2027-02-19 | Feedback Release 1 | Sửa lỗi/UX và ưu tiên feedback đầu tiên sau Tết. | Release
v0.5.0-beta.3 | 2027-03-05 | Feedback Release 2 | Cải thiện detection/UX/notifications theo feedback + dữ liệu beta. | Release
v0.5.0-beta.4 | 2027-03-19 | Feedback Release 3 | Release feedback cuối trước data freeze. | Release
DATA-FREEZE | 2027-03-31 | Data & Feedback Freeze | Chốt tập dữ liệu/feedback dùng cho phân tích và báo cáo thực nghiệm. | Data freeze
v0.6.0 | 2027-04-16 | Research/Quality | Cải thiện chất lượng dựa trên phân tích dữ liệu; không làm thay đổi thiết kế cốt lõi. | Release
v0.7.0 | 2027-05-07 | Feature Complete Candidate | Hoàn tất feature đã cam kết; chỉ còn hardening và chốt số liệu. | Release
v1.0.0-rc1 | 2027-05-28 | Release Candidate | Feature freeze; regression + security + deploy + tài liệu. | Release
v1.0.0 | 2027-06-04 | Final Product Baseline | Chốt product/research/evidence trước 06/06; sau đó chỉ critical hotfix. | Release

## Weekly Tracker
Cycle | Start | End | Phase | Owner | WP | Module | Work Package | Scope | Release Target | Workload | Done | Status | Progress % | Evidence / PR / Demo | Blocker / Note | Feature IDs | Mock / Contract Boundary
B0 | 2026-09-27 | 2026-10-05 | P1 · MVP | Hùng | H-WP03 | M01 | Session & Token Security | MVP Candidate | v0.1.0 · MVP | 22 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F008, M01-F009, M01-F010, M01-F011, M01-F012, M01-F013, M01-F014, M01-F041 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
B0 | 2026-09-27 | 2026-10-05 | P1 · MVP | Khải | K-WP01 | M02 | URL Intake, Normalization, Cache & Basic Signals | MVP Candidate | v0.1.0 · MVP | 20 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F001, M02-F002, M02-F003, M02-F004, M02-F005, M02-F006, M02-F007, M02-F008 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
B0 | 2026-09-27 | 2026-10-05 | P1 · MVP | Kiên | I-WP11 | M12 | Request Controls, Authorization & Scan Dispatch | MVP Candidate | v0.1.0 · MVP | 17 | ☐ | Chưa bắt đầu | 0% |  |  | M12-F001, M12-F002, M12-F003, M12-F004, M12-F018, M12-F019 | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
B0 | 2026-09-27 | 2026-10-05 | P1 · MVP | Thắng | T-WP01 | M03 | Vietnamese Text Normalization & Evasion Handling | MVP Candidate | v0.1.0 · MVP | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F001, M03-F002, M03-F003, M03-F004, M03-F005, M03-F006, M03-F007 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W01 | 2026-10-06 | 2026-10-12 | P1 · MVP | Hùng | H-WP01 | M01 | Local Registration & Email Verification | MVP Candidate | v0.1.0 · MVP | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F001, M01-F002, M01-F003, M01-F004, M01-F005 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W01 | 2026-10-06 | 2026-10-12 | P1 · MVP | Khải | K-WP02 | M02 | Safe Fetch & SSRF Guard | MVP Candidate | v0.1.0 · MVP | 20 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F009, M02-F010, M02-F011, M02-F012, M02-F013, M02-F014, M02-F015, M02-F016 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W01 | 2026-10-06 | 2026-10-12 | P1 · MVP | Kiên | I-WP12 | M12 | Scan Lifecycle, Event Envelope, Retry & Idempotency | MVP Candidate | v0.1.0 · MVP | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M12-F005, M12-F006, M12-F007, M12-F008, M12-F012 | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
W01 | 2026-10-06 | 2026-10-12 | P1 · MVP | Thắng | T-WP02 | M03 | Async Text Scan, Scam Patterns & User Result UX | MVP Candidate | v0.1.0 · MVP | 18 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F008, M03-F009, M03-F010, M03-F011, M03-F012, M03-F013, M03-F014, M03-F015 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W02 | 2026-10-13 | 2026-10-19 | P1 · MVP | Hùng | H-WP05 | M01 | RBAC & User Administration | MVP Candidate | v0.1.0 · MVP | 16 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F021, M01-F022, M01-F023, M01-F024, M01-F025, M01-F026, M01-F027 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W02 | 2026-10-13 | 2026-10-19 | P1 · MVP | Khải | K-WP08 | M02 | URL Worker Contract & Reputation Enrichment Boundary | MVP Candidate | v0.1.0 · MVP | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F053, M02-F054, M02-F055, M02-F056 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W02 | 2026-10-13 | 2026-10-19 | P1 · MVP | Kiên | I-WP05 | M09 | Rule Evaluation Core & Result Composition | MVP Candidate | v0.1.0 · MVP | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F001, M09-F002, M09-F004, M09-F005, M09-F037 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W02 | 2026-10-13 | 2026-10-19 | P1 · MVP | Thắng | T-WP12 | M06 | RiskResult Contract & Presentation Components | MVP Candidate | v0.1.0 · MVP | 13 | ☐ | Chưa bắt đầu | 0% |  |  | M06-F011, M06-F012, M06-F013, M06-F014, M06-F020 | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
W03 | 2026-10-20 | 2026-10-26 | P1 · MVP | Hùng | H-WP07 | M01 | Abuse Protection & Account Quota | MVP Candidate | v0.1.0 · MVP | 10 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F034, M01-F035, M01-F036, M01-F037 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W03 | 2026-10-20 | 2026-10-26 | P1 · MVP | Khải | K-WP04 | M02 | TLS, Certificate & Security Header Analysis | MVP Candidate | v0.1.0 · MVP | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F024, M02-F025, M02-F026, M02-F027, M02-F028, M02-F029, M02-F030 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W03 | 2026-10-20 | 2026-10-26 | P1 · MVP | Kiên | I-WP06 | M09 | Risk Fusion Policy, Thresholds & Missing-Signal Handling | MVP Candidate | v0.1.0 · MVP | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F003, M09-F006, M09-F007, M09-F008, M09-F038, M09-F039 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W03 | 2026-10-20 | 2026-10-26 | P1 · MVP | Thắng | T-WP10 | M06 | History Query, Access Control & Pagination | MVP Candidate | v0.1.0 · MVP | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M06-F003, M06-F004, M06-F005, M06-F006 | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
W04 | 2026-10-27 | 2026-11-02 | P2 · Core Expansion | Hùng | H-WP12 | M13 | Data Privacy & Secret Baseline | Core / Expansion | v0.2.0 · Core Expansion 1 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F001, M13-F002, M13-F005, M13-F035 | shared local compose + env templates + service test doubles; no business logic ownership
W04 | 2026-10-27 | 2026-11-02 | P2 · Core Expansion | Khải | K-WP05 | M02 | HTML/Form & Web Content Analysis | Core / Expansion | v0.2.0 · Core Expansion 1 | 17 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F031, M02-F032, M02-F033, M02-F034, M02-F035, M02-F036, M02-F037, M02-F038 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W04 | 2026-10-27 | 2026-11-02 | P2 · Core Expansion | Kiên | I-WP15 | M14 | Security & Business Audit Capture | Core / Expansion | v0.2.0 · Core Expansion 1 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M14-F001, M14-F002, M14-F003, M14-F011 | InMemoryAuditPort + mock admin/security events + correlation fixtures
W04 | 2026-10-27 | 2026-11-02 | P2 · Core Expansion | Thắng | T-WP07 | M03 | Text Input Privacy & Worker Contract | Core / Expansion | v0.2.0 · Core Expansion 1 | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F044, M03-F045, M03-F046, M03-F047, M03-F048 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W05 | 2026-11-03 | 2026-11-09 | P2 · Core Expansion | Hùng | H-WP13 | M13 | Local Runtime, Containers & Service Readiness | Core / Expansion | v0.2.0 · Core Expansion 1 | 18 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F003, M13-F004, M13-F006, M13-F007, M13-F008, M13-F009, M13-F010, M13-F011 | shared local compose + env templates + service test doubles; no business logic ownership
W05 | 2026-11-03 | 2026-11-09 | P2 · Core Expansion | Khải | K-WP09 | M04 | Phone Reputation Check | Core / Expansion | v0.2.0 · Core Expansion 1 | 17 | ☐ | Chưa bắt đầu | 0% |  |  | M04-F001, M04-F002, M04-F003, M04-F004, M04-F005, M04-F006, M04-F007, M04-F008 | MockThreatQuery + entity fixtures + fake scan-platform adapter
W05 | 2026-11-03 | 2026-11-09 | P2 · Core Expansion | Kiên | I-WP04 | M08 | Core ThreatQuery & Deferred Reputation Enrichment | Core / Expansion | v0.2.0 · Core Expansion 1 | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M08-F025, M08-F026, M08-F027 | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
W05 | 2026-11-03 | 2026-11-09 | P2 · Core Expansion | Thắng | T-WP03 | M03 | Entity Extraction from Text | Core / Expansion | v0.2.0 · Core Expansion 1 | 20 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F016, M03-F017, M03-F018, M03-F019, M03-F020, M03-F021, M03-F022, M03-F023 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W06 | 2026-11-10 | 2026-11-16 | P2 · Core Expansion | Hùng | H-WP17 | M13 | Core Infrastructure Topology, Storage & Network Boundaries | Core / Expansion | v0.2.0 · Core Expansion 1 | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F030, M13-F031, M13-F032, M13-F033, M13-F034 | shared local compose + env templates + service test doubles; no business logic ownership
W06 | 2026-11-10 | 2026-11-16 | P2 · Core Expansion | Khải | K-WP10 | M04 | Bank Account Reputation Check | Core / Expansion | v0.2.0 · Core Expansion 1 | 17 | ☐ | Chưa bắt đầu | 0% |  |  | M04-F009, M04-F010, M04-F011, M04-F012, M04-F013, M04-F014, M04-F015, M04-F016 | MockThreatQuery + entity fixtures + fake scan-platform adapter
W06 | 2026-11-10 | 2026-11-16 | P2 · Core Expansion | Kiên | I-WP13 | M12 | Nested Scan Orchestration & Derived Indicators | Core / Expansion | v0.2.0 · Core Expansion 1 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M12-F009, M12-F010, M12-F011, M12-F017 | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
W06 | 2026-11-10 | 2026-11-16 | P2 · Core Expansion | Thắng | T-WP04 | M03 | Scam Taxonomy & User-facing Classification | Core / Expansion | v0.2.0 · Core Expansion 1 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F024, M03-F025, M03-F026, M03-F027, M03-F028, M03-F029, M03-F030 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W07 | 2026-11-17 | 2026-11-23 | P2 · Core Expansion | Hùng | H-WP10 | M10 | Notification Contract, Routing & Channel Abstraction | Core / Expansion | v0.3.0 · Core Expansion 2 | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M10-F008, M10-F010, M10-F011, M10-F012 | InMemory/Console providers + MockNotificationPort + notification event fixtures
W07 | 2026-11-17 | 2026-11-23 | P2 · Core Expansion | Khải | K-WP11 | M04 | Unified Entity Scan Contract & NO_DATA Semantics | Core / Expansion | v0.3.0 · Core Expansion 2 | 6 | ☐ | Chưa bắt đầu | 0% |  |  | M04-F017, M04-F018 | MockThreatQuery + entity fixtures + fake scan-platform adapter
W07 | 2026-11-17 | 2026-11-23 | P2 · Core Expansion | Kiên | I-WP14 | M12 | AI Task Barrier, Deadline & Race Handling | Core / Expansion | v0.3.0 · Core Expansion 2 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M12-F013, M12-F014, M12-F015, M12-F016 | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
W07 | 2026-11-17 | 2026-11-23 | P2 · Core Expansion | Thắng | T-WP08 | M05 | QR/VietQR Decode, Classification & Nested Routing | Core / Expansion | v0.3.0 · Core Expansion 2 | 23 | ☐ | Chưa bắt đầu | 0% |  |  | M05-F001, M05-F002, M05-F003, M05-F004, M05-F005, M05-F006, M05-F009, M05-F010 | QR fixtures + fake scan-platform/child-scan adapter; SSRF handled by M02 contract
W08 | 2026-11-24 | 2026-11-30 | P2 · Core Expansion | Hùng | H-WP02 | M01 | External Identity, Guest Access & Account Linking | Core / Expansion | v0.3.0 · Core Expansion 2 | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F006, M01-F007, M01-F019, M01-F020 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W08 | 2026-11-24 | 2026-11-30 | P2 · Core Expansion | Khải | K-WP12 | M07 | Community Report Submission & Evidence | Core / Expansion | v0.3.0 · Core Expansion 2 | 17 | ☐ | Chưa bắt đầu | 0% |  |  | M07-F001, M07-F002, M07-F003, M07-F004, M07-F005, M07-F006, M07-F007, M07-F008 | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
W08 | 2026-11-24 | 2026-11-30 | P2 · Core Expansion | Kiên | I-WP01 | M08 | Threat Feed Ingestion & Dataset Lifecycle | Core / Expansion | v0.3.0 · Core Expansion 2 | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M08-F001, M08-F002, M08-F003, M08-F004, M08-F005, M08-F006, M08-F007 | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
W08 | 2026-11-24 | 2026-11-30 | P2 · Core Expansion | Thắng | T-WP15 | M11 | AI Task/Result Contract & Worker Core | Core / Expansion | v0.3.0 · Core Expansion 2 | 21 | ☐ | Chưa bắt đầu | 0% |  |  | M11-F001, M11-F002, M11-F003, M11-F004, M11-F005, M11-F006, M11-F017, M11-F018 | FakeMessageBus + ai request/result fixtures + mock provider adapters
W09 | 2026-12-01 | 2026-12-07 | P2 · Core Expansion | Hùng | H-WP04 | M01 | Profile, Password Lifecycle & Privacy | Core / Expansion | v0.3.0 · Core Expansion 2 | 16 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F015, M01-F016, M01-F017, M01-F018, M01-F038, M01-F039, M01-F040 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W09 | 2026-12-01 | 2026-12-07 | P2 · Core Expansion | Khải | K-WP13 | M07 | Moderation Queue & Review Workflow | Core / Expansion | v0.3.0 · Core Expansion 2 | 20 | ☐ | Chưa bắt đầu | 0% |  |  | M07-F009, M07-F010, M07-F011, M07-F012, M07-F013, M07-F014, M07-F015, M07-F016, M07-F017 | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
W09 | 2026-12-01 | 2026-12-07 | P2 · Core Expansion | Kiên | I-WP02 | M08 | Whitelist / Blacklist Administration | Core / Expansion | v0.3.0 · Core Expansion 2 | 16 | ☐ | Chưa bắt đầu | 0% |  |  | M08-F008, M08-F009, M08-F010, M08-F011, M08-F012, M08-F013, M08-F014, M08-F015 | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
W09 | 2026-12-01 | 2026-12-07 | P2 · Core Expansion | Thắng | T-WP16 | M11 | AI Provider Resolver & Adapter Registry | Core / Expansion | v0.3.0 · Core Expansion 2 | 6 | ☐ | Chưa bắt đầu | 0% |  |  | M11-F009, M11-F019, M11-F020 | FakeMessageBus + ai request/result fixtures + mock provider adapters
W10 | 2026-12-08 | 2026-12-14 | P2 · Core Expansion | Hùng | H-WP11 | M10 | Notification Endpoints, Preferences, Templates & Secret Safety | Core / Expansion | v0.4.0 · Beta Candidate | 10 | ☐ | Chưa bắt đầu | 0% |  |  | M10-F013, M10-F014, M10-F015, M10-F016, M10-F018 | InMemory/Console providers + MockNotificationPort + notification event fixtures
W10 | 2026-12-08 | 2026-12-14 | P2 · Core Expansion | Khải | K-WP15 | M07 | Verified Report → Threat/Reputation Signal Bridge | Core / Expansion | v0.4.0 · Beta Candidate | 6 | ☐ | Chưa bắt đầu | 0% |  |  | M07-F025, M07-F026 | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
W10 | 2026-12-08 | 2026-12-14 | P2 · Core Expansion | Kiên | I-WP03 | M08 | Risk Entity Registry & Evidence Consolidation | Core / Expansion | v0.4.0 · Beta Candidate | 18 | ☐ | Chưa bắt đầu | 0% |  |  | M08-F016, M08-F017, M08-F018, M08-F019, M08-F020, M08-F021, M08-F022, M08-F023, M08-F024 | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
W10 | 2026-12-08 | 2026-12-14 | P2 · Core Expansion | Thắng | T-WP18 | M11 | AI Evaluation Dataset, Metrics & Calibration | Core / Expansion | v0.4.0 · Beta Candidate | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M11-F010, M11-F011, M11-F012, M11-F013, M11-F014, M11-F015, M11-F016 | FakeMessageBus + ai request/result fixtures + mock provider adapters
W11 | 2026-12-15 | 2026-12-21 | P3 · Beta Preparation | Hùng | H-WP09 | M10 | Notification Delivery Reliability | Core / Expansion | v0.4.0 · Beta Candidate | 6 | ☐ | Chưa bắt đầu | 0% |  |  | M10-F003, M10-F009, M10-F017 | InMemory/Console providers + MockNotificationPort + notification event fixtures
W11 | 2026-12-15 | 2026-12-21 | P3 · Beta Preparation | Khải | K-WP03 | M02 | Redirect Chain Analysis | Core / Expansion | v0.4.0 · Beta Candidate | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F017, M02-F018, M02-F019, M02-F020, M02-F021, M02-F022, M02-F023 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W11 | 2026-12-15 | 2026-12-21 | P3 · Beta Preparation | Kiên | I-WP07 | M09 | Rule Repository & Admin Management | Core / Expansion | v0.4.0 · Beta Candidate | 16 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F009, M09-F010, M09-F011, M09-F012, M09-F013, M09-F014, M09-F015, M09-F016 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W11 | 2026-12-15 | 2026-12-21 | P3 · Beta Preparation | Thắng | T-WP11 | M06 | History Retention & User Management | Core / Expansion | v0.4.0 · Beta Candidate | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M06-F001, M06-F002, M06-F007, M06-F008, M06-F009, M06-F010 | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
W14 | 2027-01-05 | 2027-01-11 | P3 · Beta Preparation | Hùng | H-WP14 | M13 | CI/CD & Dependency Quality Gates | Core / Expansion | v0.5.0-beta.1 · Public Beta | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F012, M13-F013, M13-F014, M13-F015, M13-F016, M13-F017, M13-F020 | shared local compose + env templates + service test doubles; no business logic ownership
W14 | 2027-01-05 | 2027-01-11 | P3 · Beta Preparation | Khải | K-WP06 | M02 | Brand Impersonation & Typosquatting Detection | Core / Expansion | v0.5.0-beta.1 · Public Beta | 14 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F039, M02-F040, M02-F041, M02-F042, M02-F043, M02-F044, M02-F045 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W14 | 2027-01-05 | 2027-01-11 | P3 · Beta Preparation | Kiên | I-WP09 | M09 | Rule Versioning, History & Rollback | Core / Expansion | v0.5.0-beta.1 · Public Beta | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F023, M09-F024, M09-F025, M09-F026, M09-F027, M09-F028 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W14 | 2027-01-05 | 2027-01-11 | P3 · Beta Preparation | Thắng | T-WP14 | M06 | Async Export & Admin Reporting | Core / Expansion | v0.5.0-beta.1 · Public Beta | 5 | ☐ | Chưa bắt đầu | 0% |  |  | M06-F016, M06-F019, M06-F021 | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
W15 | 2027-01-12 | 2027-01-18 | P3 · Beta Preparation | Hùng | H-WP08 | M10 | Notification Center & User Follow-up UX | Core / Expansion | v0.5.0-beta.1 · Public Beta | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M10-F001, M10-F002, M10-F004, M10-F005, M10-F006, M10-F007 | InMemory/Console providers + MockNotificationPort + notification event fixtures
W15 | 2027-01-12 | 2027-01-18 | P3 · Beta Preparation | Khải | K-WP07 | M02 | Web Evidence Capture & Retention | Core / Expansion | v0.5.0-beta.1 · Public Beta | 11 | ☐ | Chưa bắt đầu | 0% |  |  | M02-F046, M02-F047, M02-F048, M02-F049, M02-F050, M02-F051, M02-F052 | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
W15 | 2027-01-12 | 2027-01-18 | P3 · Beta Preparation | Kiên | I-WP08 | M09 | Rule Preview, Simulation & Shadow Evaluation | Core / Expansion | v0.5.0-beta.1 · Public Beta | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F017, M09-F018, M09-F019, M09-F020, M09-F021, M09-F022 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W15 | 2027-01-12 | 2027-01-18 | P3 · Beta Preparation | Thắng | T-WP13 | M06 | Result Sharing & External Consumption | Core / Expansion | v0.5.0-beta.1 · Public Beta | 4 | ☐ | Chưa bắt đầu | 0% |  |  | M06-F015, M06-F017, M06-F018 | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
W20 | 2027-02-16 | 2027-02-22 | P4 · Beta Feedback & Data | Hùng | H-WP16 | M13 | Accessibility, i18n & Mobile Entry Surfaces | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 15 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F021, M13-F022, M13-F023, M13-F024, M13-F025, M13-F026, M13-F027, M13-F028, M13-F029 | shared local compose + env templates + service test doubles; no business logic ownership
W20 | 2027-02-16 | 2027-02-22 | P4 · Beta Feedback & Data | Khải | K-WP14 | M07 | Reporter Reputation & Abuse Controls | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 10 | ☐ | Chưa bắt đầu | 0% |  |  | M07-F018, M07-F019, M07-F020, M07-F021, M07-F022, M07-F023, M07-F024 | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
W20 | 2027-02-16 | 2027-02-22 | P4 · Beta Feedback & Data | Kiên | I-WP10 | M09 | Risk & Scam Operations Analytics | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 13 | ☐ | Chưa bắt đầu | 0% |  |  | M09-F029, M09-F030, M09-F031, M09-F032, M09-F033, M09-F034, M09-F035, M09-F036 | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
W20 | 2027-02-16 | 2027-02-22 | P4 · Beta Feedback & Data | Thắng | T-WP05 | M03 | Keyword Dictionary Administration | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 12 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F031, M03-F032, M03-F033, M03-F034, M03-F035, M03-F036, M03-F037 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W21 | 2027-02-23 | 2027-03-01 | P4 · Beta Feedback & Data | Hùng | H-WP15 | M13 | Runtime Metrics & Alerting | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 2 | ☐ | Chưa bắt đầu | 0% |  |  | M13-F018, M13-F019 | shared local compose + env templates + service test doubles; no business logic ownership
W21 | 2027-02-23 | 2027-03-01 | P4 · Beta Feedback & Data | Kiên | I-WP16 | M14 | Cross-Pipeline Correlation & Failure Trace | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 5 | ☐ | Chưa bắt đầu | 0% |  |  | M14-F008, M14-F009 | InMemoryAuditPort + mock admin/security events + correlation fixtures
W21 | 2027-02-23 | 2027-03-01 | P4 · Beta Feedback & Data | Thắng | T-WP06 | M03 | Multi-turn Conversation Analysis | Core / Expansion | v0.5.0-beta.3 · Feedback Release 2 | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M03-F038, M03-F039, M03-F040, M03-F041, M03-F042, M03-F043 | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
W22 | 2027-03-02 | 2027-03-08 | P4 · Beta Feedback & Data | Hùng | H-WP06 | M01 | Advanced Account Security | Core / Expansion | v0.5.0-beta.4 · Feedback Release 3 | 9 | ☐ | Chưa bắt đầu | 0% |  |  | M01-F028, M01-F029, M01-F030, M01-F031, M01-F032, M01-F033 | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
W22 | 2027-03-02 | 2027-03-08 | P4 · Beta Feedback & Data | Kiên | I-WP17 | M14 | Audit Query, Operations UI & Investigation | Core / Expansion | v0.5.0-beta.4 · Feedback Release 3 | 8 | ☐ | Chưa bắt đầu | 0% |  |  | M14-F004, M14-F005, M14-F006, M14-F007, M14-F010 | InMemoryAuditPort + mock admin/security events + correlation fixtures
W22 | 2027-03-02 | 2027-03-08 | P4 · Beta Feedback & Data | Thắng | T-WP17 | M11 | AI Safety, Prompt/Output Guardrails & Cache Options | Core / Expansion | v0.5.0-beta.4 · Feedback Release 3 | 2 | ☐ | Chưa bắt đầu | 0% |  |  | M11-F007, M11-F008 | FakeMessageBus + ai request/result fixtures + mock provider adapters
W23 | 2027-03-09 | 2027-03-15 | P4 · Beta Feedback & Data | Thắng | T-WP09 | M05 | Advanced QR Safety Checks | Core / Expansion | v0.5.0-beta.4 · Feedback Release 3 | 2 | ☐ | Chưa bắt đầu | 0% |  |  | M05-F007, M05-F008 | QR fixtures + fake scan-platform/child-scan adapter; SSRF handled by M02 contract
W28 | 2027-04-13 | 2027-04-19 | P5 · Research, Quality & Completion | Hùng | H-FWP01 | FUTURE | Future Entitlements, Plans & Subscription Boundary | Optional / Future | v0.7.0 · Feature Complete Candidate | 4 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F025, FUTURE-F026, FUTURE-F027, FUTURE-F028 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W28 | 2027-04-13 | 2027-04-19 | P5 · Research, Quality & Completion | Khải | K-FWP01 | FUTURE | Browser Extension Protection Surface | Optional / Future | v0.7.0 · Feature Complete Candidate | 6 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F001, FUTURE-F002, FUTURE-F003, FUTURE-F004, FUTURE-F005, FUTURE-F006 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W29 | 2027-04-20 | 2027-04-26 | P5 · Research, Quality & Completion | Kiên | I-FWP01 | FUTURE | Knowledge Library & Editorial Workflow | Optional / Future | v0.7.0 · Feature Complete Candidate | 6 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F007, FUTURE-F008, FUTURE-F009, FUTURE-F010, FUTURE-F011, FUTURE-F012 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W29 | 2027-04-20 | 2027-04-26 | P5 · Research, Quality & Completion | Thắng | T-FWP01 | FUTURE | Scam Q&A Assistant | Optional / Future | v0.7.0 · Feature Complete Candidate | 6 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F013, FUTURE-F014, FUTURE-F015, FUTURE-F016, FUTURE-F017, FUTURE-F018 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W32 | 2027-05-11 | 2027-05-17 | P6 · Final Product/Data Freeze | Hùng | H-FWP02 | FUTURE | Future Usage, Credit Ledger & API Credentials | Optional / Future | v1.0.0-rc1 · Release Candidate | 5 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F029, FUTURE-F030, FUTURE-F031, FUTURE-F032, FUTURE-F033 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W32 | 2027-05-11 | 2027-05-17 | P6 · Final Product/Data Freeze | Khải | K-FWP02 | FUTURE | Community Contribution Gamification | Optional / Future | v1.0.0-rc1 · Release Candidate | 3 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F021, FUTURE-F022, FUTURE-F023 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W33 | 2027-05-18 | 2027-05-24 | P6 · Final Product/Data Freeze | Kiên | I-FWP02 | FUTURE | Anti-Scam Quiz & Learning Evaluation | Optional / Future | v1.0.0-rc1 · Release Candidate | 2 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F019, FUTURE-F020 | Build against current public ports/fixtures; must not change MVP contracts until promoted
W33 | 2027-05-18 | 2027-05-24 | P6 · Final Product/Data Freeze | Thắng | T-FWP02 | FUTURE | Social Sharing for Learning/Engagement | Optional / Future | v1.0.0-rc1 · Release Candidate | 1 | ☐ | Chưa bắt đầu | 0% |  |  | FUTURE-F024 | Build against current public ports/fixtures; must not change MVP contracts until promoted

## Weekly Calendar
Cycle | Start | End | Phase | Hùng | Khải | Kiên | Thắng | Recurring / QA | Release / Milestone | GV Thứ 3 | T5 Meeting | T7 Meeting | T2 Summary
B0 | 2026-09-27 | 2026-10-05 | P1 · MVP | H-WP03 | K-WP01 | I-WP11 | T-WP01 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-10-01 | 2026-10-03 | 2026-10-05
W01 | 2026-10-06 | 2026-10-12 | P1 · MVP | H-WP01 | K-WP02 | I-WP12 | T-WP02 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-10-08 | 2026-10-10 | 2026-10-12
W02 | 2026-10-13 | 2026-10-19 | P1 · MVP | H-WP05 | K-WP08 | I-WP05 | T-WP12 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-10-15 | 2026-10-17 | 2026-10-19
W03 | 2026-10-20 | 2026-10-26 | P1 · MVP | H-WP07 | K-WP04 | I-WP06 | T-WP10 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-10-22 | 2026-10-24 | 2026-10-26
W04 | 2026-10-27 | 2026-11-02 | P2 · Core Expansion | H-WP12 | K-WP05 | I-WP15 | T-WP07 | Contract test + integration smoke + cập nhật tracker | 30/10: v0.1.0 — MVP | Có | 2026-10-29 | 2026-10-31 | 2026-11-02
W05 | 2026-11-03 | 2026-11-09 | P2 · Core Expansion | H-WP13 | K-WP09 | I-WP04 | T-WP03 | Contract test + integration smoke + cập nhật tracker | 09/11: Đăng ký đề tài KLTN window bắt đầu | Tuỳ chọn | 2026-11-05 | 2026-11-07 | 2026-11-09
W06 | 2026-11-10 | 2026-11-16 | P2 · Core Expansion | H-WP17 | K-WP10 | I-WP13 | T-WP04 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-11-12 | 2026-11-14 | 2026-11-16
W07 | 2026-11-17 | 2026-11-23 | P2 · Core Expansion | H-WP10 | K-WP11 | I-WP14 | T-WP08 | Contract test + integration smoke + cập nhật tracker | 20/11: v0.2.0 — Core Expansion 1 | Tuỳ chọn | 2026-11-19 | 2026-11-21 | 2026-11-23
W08 | 2026-11-24 | 2026-11-30 | P2 · Core Expansion | H-WP02 | K-WP12 | I-WP01 | T-WP15 | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-11-26 | 2026-11-28 | 2026-11-30
W09 | 2026-12-01 | 2026-12-07 | P2 · Core Expansion | H-WP04 | K-WP13 | I-WP02 | T-WP16 | Contract test + integration smoke + cập nhật tracker | — | Tuỳ chọn | 2026-12-03 | 2026-12-05 | 2026-12-07
W10 | 2026-12-08 | 2026-12-14 | P2 · Core Expansion | H-WP11 | K-WP15 | I-WP03 | T-WP18 | Contract test + integration smoke + cập nhật tracker | 11/12: v0.3.0 — Core Expansion 2 | Có | 2026-12-10 | 2026-12-12 | 2026-12-14
W11 | 2026-12-15 | 2026-12-21 | P3 · Beta Preparation | H-WP09 | K-WP03 | I-WP07 | T-WP11 | Contract test + integration smoke + cập nhật tracker | — | Tuỳ chọn | 2026-12-17 | 2026-12-19 | 2026-12-21
W12 | 2026-12-22 | 2026-12-28 | P3 · Beta Preparation | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Contract test + integration smoke + cập nhật tracker | — | Có | 2026-12-24 | 2026-12-26 | 2026-12-28
W13 | 2026-12-29 | 2027-01-04 | P3 · Beta Preparation | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Contract test + integration smoke + cập nhật tracker | — | Tuỳ chọn | 2026-12-31 | 2027-01-02 | 2027-01-04
W14 | 2027-01-05 | 2027-01-11 | P3 · Beta Preparation | H-WP14 | K-WP06 | I-WP09 | T-WP14 | Contract test + integration smoke + cập nhật tracker | 08/01: v0.4.0 — Beta Candidate | Có | 2027-01-07 | 2027-01-09 | 2027-01-11
W15 | 2027-01-12 | 2027-01-18 | P3 · Beta Preparation | H-WP08 | K-WP07 | I-WP08 | T-WP13 | Contract test + integration smoke + cập nhật tracker | — | Tuỳ chọn | 2027-01-14 | 2027-01-16 | 2027-01-18
W16 | 2027-01-19 | 2027-01-25 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | 22/01: v0.5.0-beta.1 — Public Beta | Có | 2027-01-21 | 2027-01-23 | 2027-01-25
W17 | 2027-01-26 | 2027-02-01 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | — | Tuỳ chọn | 2027-01-28 | 2027-01-30 | 2027-02-01
W18 | 2027-02-02 | 2027-02-08 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | — | Có | 2027-02-04 | 2027-02-06 | 2027-02-08
W19 | 2027-02-09 | 2027-02-15 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | — | Tuỳ chọn | 2027-02-11 | 2027-02-13 | 2027-02-15
W20 | 2027-02-16 | 2027-02-22 | P4 · Beta Feedback & Data | H-WP16 | K-WP14 | I-WP10 | T-WP05 | Feedback triage + data quality check + cập nhật issue backlog | 19/02: v0.5.0-beta.2 — Feedback Release 1 ¦ 22/02: Nộp đề cương KLTN window bắt đầu | Có | 2027-02-18 | 2027-02-20 | 2027-02-22
W21 | 2027-02-23 | 2027-03-01 | P4 · Beta Feedback & Data | H-WP15 | Buffer / integration / spillover | I-WP16 | T-WP06 | Feedback triage + data quality check + cập nhật issue backlog | — | Tuỳ chọn | 2027-02-25 | 2027-02-27 | 2027-03-01
W22 | 2027-03-02 | 2027-03-08 | P4 · Beta Feedback & Data | H-WP06 | Buffer / integration / spillover | I-WP17 | T-WP17 | Feedback triage + data quality check + cập nhật issue backlog | 05/03: v0.5.0-beta.3 — Feedback Release 2 | Có | 2027-03-04 | 2027-03-06 | 2027-03-08
W23 | 2027-03-09 | 2027-03-15 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | T-WP09 | Feedback triage + data quality check + cập nhật issue backlog | — | Tuỳ chọn | 2027-03-11 | 2027-03-13 | 2027-03-15
W24 | 2027-03-16 | 2027-03-22 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | 19/03: v0.5.0-beta.4 — Feedback Release 3 | Có | 2027-03-18 | 2027-03-20 | 2027-03-22
W25 | 2027-03-23 | 2027-03-29 | P4 · Beta Feedback & Data | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Feedback triage + data quality check + cập nhật issue backlog | — | Tuỳ chọn | 2027-03-25 | 2027-03-27 | 2027-03-29
W26 | 2027-03-30 | 2027-04-05 | P5 · Research, Quality & Completion | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | 31/03: DATA-FREEZE — Data & Feedback Freeze | Có | 2027-04-01 | 2027-04-03 | 2027-04-05
W27 | 2027-04-06 | 2027-04-12 | P5 · Research, Quality & Completion | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | — | Tuỳ chọn | 2027-04-08 | 2027-04-10 | 2027-04-12
W28 | 2027-04-13 | 2027-04-19 | P5 · Research, Quality & Completion | H-FWP01 | K-FWP01 | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | 16/04: v0.6.0 — Research/Quality ¦ 19/04: Báo cáo tiến độ / kỳ thi HK2 | Có | 2027-04-15 | 2027-04-17 | 2027-04-19
W29 | 2027-04-20 | 2027-04-26 | P5 · Research, Quality & Completion | Buffer / integration / spillover | Buffer / integration / spillover | I-FWP01 | T-FWP01 | Regression/metrics + viết báo cáo song song + evidence capture | — | Tuỳ chọn | 2027-04-22 | 2027-04-24 | 2027-04-26
W30 | 2027-04-27 | 2027-05-03 | P5 · Research, Quality & Completion | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | — | Có | 2027-04-29 | 2027-05-01 | 2027-05-03
W31 | 2027-05-04 | 2027-05-10 | P5 · Research, Quality & Completion | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | 07/05: v0.7.0 — Feature Complete Candidate | Tuỳ chọn | 2027-05-06 | 2027-05-08 | 2027-05-10
W32 | 2027-05-11 | 2027-05-17 | P6 · Final Product/Data Freeze | H-FWP02 | K-FWP02 | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | — | Có | 2027-05-13 | 2027-05-15 | 2027-05-17
W33 | 2027-05-18 | 2027-05-24 | P6 · Final Product/Data Freeze | Buffer / integration / spillover | Buffer / integration / spillover | I-FWP02 | T-FWP02 | Regression/metrics + viết báo cáo song song + evidence capture | — | Có | 2027-05-20 | 2027-05-22 | 2027-05-24
W34 | 2027-05-25 | 2027-05-31 | P6 · Final Product/Data Freeze | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Regression/metrics + viết báo cáo song song + evidence capture | 28/05: v1.0.0-rc1 — Release Candidate | Có | 2027-05-27 | 2027-05-29 | 2027-05-31
W35 | 2027-06-01 | 2027-06-07 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | 04/06: v1.0.0 — Final Product Baseline ¦ 06/06: Internal completion deadline: product + data + experiments complete | Có | 2027-06-03 | 2027-06-05 | 2027-06-07
W36 | 2027-06-08 | 2027-06-14 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | — | Có | 2027-06-10 | 2027-06-12 | 2027-06-14
W37 | 2027-06-15 | 2027-06-21 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | — | Có | 2027-06-17 | 2027-06-19 | 2027-06-21
W38 | 2027-06-22 | 2027-06-28 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | 28/06: Nộp đơn bảo vệ + bản cuối window | Có | 2027-06-24 | 2027-06-26 | 2027-06-28
W39 | 2027-06-29 | 2027-07-05 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | — | Có | 2027-07-01 | 2027-07-03 | 2027-07-05
W40 | 2027-07-06 | 2027-07-12 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | 12/07: Phản biện | Có | 2027-07-08 | 2027-07-10 | 2027-07-12
W41 | 2027-07-13 | 2027-07-19 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | 19/07: Bảo vệ KLTN window bắt đầu | Tuỳ chọn | 2027-07-15 | 2027-07-17 | 2027-07-19
W42 | 2027-07-20 | 2027-07-26 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | — | Có | 2027-07-22 | 2027-07-24 | 2027-07-26
W43 | 2027-07-27 | 2027-08-02 | P7 · Thesis Finalization & Defense | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Buffer / integration / spillover | Không thêm feature; chỉ critical hotfix + báo cáo/slide/rehearsal | — | Tuỳ chọn | 2027-07-29 | 2027-07-31 | 2027-08-02

## 2 tuần đầu
Cycle | Period | Owner | WP | Goal | Deliverable | Evidence | Done | Status | Note
B0 | 27/09/2026 → 05/10/2026 | Hùng | H-WP03 | Session & Token Security | auth_session; JWT access 15'; opaque refresh; token hash; rotation/reuse detection; revoke current/all session; tests. | Integration test login→refresh→rotate→reuse=401; DB không lưu raw refresh token. | ☐ | Chưa bắt đầu
B0 | 27/09/2026 → 05/10/2026 | Khải | K-WP01 | URL Intake, Normalization, Cache & Basic Signals | POST /v1/scans/url contract; URL normalize/hash; cache/result path; basic lexical signals; worker fixture. | 15 URL variants normalize đúng; cache hit/miss test; fixture worker-result pass contract. | ☐ | Chưa bắt đầu
B0 | 27/09/2026 → 05/10/2026 | Kiên | I-WP11 | Request Controls, Authorization & Scan Dispatch | validate input; guest/user AccessContext; create ScanRequest; dispatch async bằng FakeMessageBus; 202 + scanId. | Contract test 4 scan types; unauthorized/invalid input đúng; dispatch event đúng schema. | ☐ | Chưa bắt đầu
B0 | 27/09/2026 → 05/10/2026 | Thắng | T-WP01 | Vietnamese Text Normalization & Evasion Handling | normalization pipeline tiếng Việt; obfuscation/evasion fixtures; unit tests; output dùng được bởi text worker. | Bộ fixture scam/benign/evasion chạy xanh; normalization không phá phone/account/url extraction. | ☐ | Chưa bắt đầu
B0 | 27/09/2026 → 05/10/2026 | Cả nhóm | TEAM-C01 | Contract Freeze v1 + baseline audit | Freeze AccessContext, ScanJobEnvelope, WorkerAnalysisResult, RiskResult, NotificationPort; rà repo để tick phần đã làm trước 27/09. | Contract files merge main; tracker status được cập nhật; smoke test local stack. | ☐ | Chưa bắt đầu
W01 | 06/10/2026 → 12/10/2026 | Hùng | H-WP01 | Local Registration & Email Verification | register Local; password hash; email normalization/unique; verification challenge; resend rate limit qua MockNotificationPort. | Register/login test; challenge expiry/single-use test; không log password/OTP. | ☐ | Chưa bắt đầu
W01 | 06/10/2026 → 12/10/2026 | Khải | K-WP02 | Safe Fetch & SSRF Guard | allow http/https; DNS resolve trước connect; private/link-local block; redirect re-check; size/timeout limits; attack tests. | 169.254.169.254/localhost/DNS rebinding/redirect nội bộ đều bị chặn. | ☐ | Chưa bắt đầu
W01 | 06/10/2026 → 12/10/2026 | Kiên | I-WP12 | Scan Lifecycle, Event Envelope, Retry & Idempotency | PENDING→PROCESSING→COMPLETED/FAILED; event envelope; dedupe eventId; retry/DLQ; no infinite processing. | Race/idempotency/retry test xanh; duplicate event không tạo duplicate state transition. | ☐ | Chưa bắt đầu
W01 | 06/10/2026 → 12/10/2026 | Thắng | T-WP02 | Async Text Scan, Scam Patterns & User Result UX | POST /v1/scans/text; MESSAGE/TRANSACTION_POST; fake bus worker flow; evidence/result UX theo RiskResult mock. | Submit→202 scanId→PROCESSING→RiskResult fixture; UI render evidence/recommendation. | ☐ | Chưa bắt đầu
W01 | 06/10/2026 → 12/10/2026 | Cả nhóm | TEAM-C02 | Integration checkpoint 1 | Nối auth context → scan dispatch → text/url worker fixture → RiskResult mock; fix contract mismatches only. | End-to-end smoke test chạy được bằng mock/fake, không cần AI/threat thật. | ☐ | Chưa bắt đầu

## WP Catalog
WP | Owner | Module | Work Package | Feature IDs | P0 | P1 | P2 | Workload | Scope | Mock / Contract Boundary
H-WP01 | Hùng | M01 | Local Registration & Email Verification | M01-F001, M01-F002, M01-F003, M01-F004, M01-F005 | 4 | 1 | 0 | 14 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP02 | Hùng | M01 | External Identity, Guest Access & Account Linking | M01-F006, M01-F007, M01-F019, M01-F020 | 3 | 1 | 0 | 11 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP03 | Hùng | M01 | Session & Token Security | M01-F008, M01-F009, M01-F010, M01-F011, M01-F012, M01-F013, M01-F014, M01-F041 | 6 | 2 | 0 | 22 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP04 | Hùng | M01 | Profile, Password Lifecycle & Privacy | M01-F015, M01-F016, M01-F017, M01-F018, M01-F038, M01-F039, M01-F040 | 3 | 3 | 1 | 16 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP05 | Hùng | M01 | RBAC & User Administration | M01-F021, M01-F022, M01-F023, M01-F024, M01-F025, M01-F026, M01-F027 | 3 | 3 | 1 | 16 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP06 | Hùng | M01 | Advanced Account Security | M01-F028, M01-F029, M01-F030, M01-F031, M01-F032, M01-F033 | 0 | 3 | 3 | 9 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP07 | Hùng | M01 | Abuse Protection & Account Quota | M01-F034, M01-F035, M01-F036, M01-F037 | 3 | 0 | 1 | 10 | Core | MockNotificationPort + FakeAccessContext/EntitlementContext; external IdP behind adapter
H-WP08 | Hùng | M10 | Notification Center & User Follow-up UX | M10-F001, M10-F002, M10-F004, M10-F005, M10-F006, M10-F007 | 0 | 3 | 3 | 9 | Core | InMemory/Console providers + MockNotificationPort + notification event fixtures
H-WP09 | Hùng | M10 | Notification Delivery Reliability | M10-F003, M10-F009, M10-F017 | 0 | 3 | 0 | 6 | Core | InMemory/Console providers + MockNotificationPort + notification event fixtures
H-WP10 | Hùng | M10 | Notification Contract, Routing & Channel Abstraction | M10-F008, M10-F010, M10-F011, M10-F012 | 3 | 1 | 0 | 11 | Core | InMemory/Console providers + MockNotificationPort + notification event fixtures
H-WP11 | Hùng | M10 | Notification Endpoints, Preferences, Templates & Secret Safety | M10-F013, M10-F014, M10-F015, M10-F016, M10-F018 | 1 | 3 | 1 | 10 | Core | InMemory/Console providers + MockNotificationPort + notification event fixtures
H-WP12 | Hùng | M13 | Data Privacy & Secret Baseline | M13-F001, M13-F002, M13-F005, M13-F035 | 4 | 0 | 0 | 12 | Core | shared local compose + env templates + service test doubles; no business logic ownership
H-WP13 | Hùng | M13 | Local Runtime, Containers & Service Readiness | M13-F003, M13-F004, M13-F006, M13-F007, M13-F008, M13-F009, M13-F010, M13-F011 | 3 | 4 | 1 | 18 | Core | shared local compose + env templates + service test doubles; no business logic ownership
H-WP14 | Hùng | M13 | CI/CD & Dependency Quality Gates | M13-F012, M13-F013, M13-F014, M13-F015, M13-F016, M13-F017, M13-F020 | 2 | 4 | 1 | 15 | Core | shared local compose + env templates + service test doubles; no business logic ownership
H-WP15 | Hùng | M13 | Runtime Metrics & Alerting | M13-F018, M13-F019 | 0 | 0 | 2 | 2 | Core | shared local compose + env templates + service test doubles; no business logic ownership
H-WP16 | Hùng | M13 | Accessibility, i18n & Mobile Entry Surfaces | M13-F021, M13-F022, M13-F023, M13-F024, M13-F025, M13-F026, M13-F027, M13-F028, M13-F029 | 1 | 4 | 4 | 15 | Core | shared local compose + env templates + service test doubles; no business logic ownership
H-WP17 | Hùng | M13 | Core Infrastructure Topology, Storage & Network Boundaries | M13-F030, M13-F031, M13-F032, M13-F033, M13-F034 | 5 | 0 | 0 | 15 | Core | shared local compose + env templates + service test doubles; no business logic ownership
K-WP01 | Khải | M02 | URL Intake, Normalization, Cache & Basic Signals | M02-F001, M02-F002, M02-F003, M02-F004, M02-F005, M02-F006, M02-F007, M02-F008 | 5 | 2 | 1 | 20 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP02 | Khải | M02 | Safe Fetch & SSRF Guard | M02-F009, M02-F010, M02-F011, M02-F012, M02-F013, M02-F014, M02-F015, M02-F016 | 5 | 2 | 1 | 20 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP03 | Khải | M02 | Redirect Chain Analysis | M02-F017, M02-F018, M02-F019, M02-F020, M02-F021, M02-F022, M02-F023 | 2 | 3 | 2 | 14 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP04 | Khải | M02 | TLS, Certificate & Security Header Analysis | M02-F024, M02-F025, M02-F026, M02-F027, M02-F028, M02-F029, M02-F030 | 2 | 3 | 2 | 14 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP05 | Khải | M02 | HTML/Form & Web Content Analysis | M02-F031, M02-F032, M02-F033, M02-F034, M02-F035, M02-F036, M02-F037, M02-F038 | 3 | 3 | 2 | 17 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP06 | Khải | M02 | Brand Impersonation & Typosquatting Detection | M02-F039, M02-F040, M02-F041, M02-F042, M02-F043, M02-F044, M02-F045 | 2 | 3 | 2 | 14 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP07 | Khải | M02 | Web Evidence Capture & Retention | M02-F046, M02-F047, M02-F048, M02-F049, M02-F050, M02-F051, M02-F052 | 0 | 4 | 3 | 11 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP08 | Khải | M02 | URL Worker Contract & Reputation Enrichment Boundary | M02-F053, M02-F054, M02-F055, M02-F056 | 4 | 0 | 0 | 12 | Core | FakeMessageBus + MockThreatQuery + RiskResult/worker fixtures; no direct DB/core call from worker
K-WP09 | Khải | M04 | Phone Reputation Check | M04-F001, M04-F002, M04-F003, M04-F004, M04-F005, M04-F006, M04-F007, M04-F008 | 3 | 3 | 2 | 17 | Core | MockThreatQuery + entity fixtures + fake scan-platform adapter
K-WP10 | Khải | M04 | Bank Account Reputation Check | M04-F009, M04-F010, M04-F011, M04-F012, M04-F013, M04-F014, M04-F015, M04-F016 | 3 | 3 | 2 | 17 | Core | MockThreatQuery + entity fixtures + fake scan-platform adapter
K-WP11 | Khải | M04 | Unified Entity Scan Contract & NO_DATA Semantics | M04-F017, M04-F018 | 2 | 0 | 0 | 6 | Core | MockThreatQuery + entity fixtures + fake scan-platform adapter
K-WP12 | Khải | M07 | Community Report Submission & Evidence | M07-F001, M07-F002, M07-F003, M07-F004, M07-F005, M07-F006, M07-F007, M07-F008 | 3 | 3 | 2 | 17 | Core | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
K-WP13 | Khải | M07 | Moderation Queue & Review Workflow | M07-F009, M07-F010, M07-F011, M07-F012, M07-F013, M07-F014, M07-F015, M07-F016, M07-F017 | 4 | 3 | 2 | 20 | Core | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
K-WP14 | Khải | M07 | Reporter Reputation & Abuse Controls | M07-F018, M07-F019, M07-F020, M07-F021, M07-F022, M07-F023, M07-F024 | 0 | 3 | 4 | 10 | Core | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
K-WP15 | Khải | M07 | Verified Report → Threat/Reputation Signal Bridge | M07-F025, M07-F026 | 2 | 0 | 0 | 6 | Core | Seed report fixtures + MockThreatQuery + MockNotificationPort + InMemoryAuditPort
I-WP01 | Kiên | M08 | Threat Feed Ingestion & Dataset Lifecycle | M08-F001, M08-F002, M08-F003, M08-F004, M08-F005, M08-F006, M08-F007 | 0 | 4 | 3 | 11 | Core | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
I-WP02 | Kiên | M08 | Whitelist / Blacklist Administration | M08-F008, M08-F009, M08-F010, M08-F011, M08-F012, M08-F013, M08-F014, M08-F015 | 2 | 4 | 2 | 16 | Core | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
I-WP03 | Kiên | M08 | Risk Entity Registry & Evidence Consolidation | M08-F016, M08-F017, M08-F018, M08-F019, M08-F020, M08-F021, M08-F022, M08-F023, M08-F024 | 3 | 3 | 3 | 18 | Core | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
I-WP04 | Kiên | M08 | Core ThreatQuery & Deferred Reputation Enrichment | M08-F025, M08-F026, M08-F027 | 3 | 0 | 0 | 9 | Core | sample threat feeds + in-memory repository/cache adapter; core-only ThreatQuery contract
I-WP05 | Kiên | M09 | Rule Evaluation Core & Result Composition | M09-F001, M09-F002, M09-F004, M09-F005, M09-F037 | 5 | 0 | 0 | 15 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP06 | Kiên | M09 | Risk Fusion Policy, Thresholds & Missing-Signal Handling | M09-F003, M09-F006, M09-F007, M09-F008, M09-F038, M09-F039 | 3 | 2 | 1 | 14 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP07 | Kiên | M09 | Rule Repository & Admin Management | M09-F009, M09-F010, M09-F011, M09-F012, M09-F013, M09-F014, M09-F015, M09-F016 | 2 | 4 | 2 | 16 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP08 | Kiên | M09 | Rule Preview, Simulation & Shadow Evaluation | M09-F017, M09-F018, M09-F019, M09-F020, M09-F021, M09-F022 | 0 | 3 | 3 | 9 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP09 | Kiên | M09 | Rule Versioning, History & Rollback | M09-F023, M09-F024, M09-F025, M09-F026, M09-F027, M09-F028 | 0 | 3 | 3 | 9 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP10 | Kiên | M09 | Risk & Scam Operations Analytics | M09-F029, M09-F030, M09-F031, M09-F032, M09-F033, M09-F034, M09-F035, M09-F036 | 0 | 5 | 3 | 13 | Core | UnifiedSignalSet fixtures + deterministic policy fixtures; expose RiskEvaluationPort
I-WP11 | Kiên | M12 | Request Controls, Authorization & Scan Dispatch | M12-F001, M12-F002, M12-F003, M12-F004, M12-F018, M12-F019 | 5 | 1 | 0 | 17 | Core | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
I-WP12 | Kiên | M12 | Scan Lifecycle, Event Envelope, Retry & Idempotency | M12-F005, M12-F006, M12-F007, M12-F008, M12-F012 | 5 | 0 | 0 | 15 | Core | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
I-WP13 | Kiên | M12 | Nested Scan Orchestration & Derived Indicators | M12-F009, M12-F010, M12-F011, M12-F017 | 4 | 0 | 0 | 12 | Core | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
I-WP14 | Kiên | M12 | AI Task Barrier, Deadline & Race Handling | M12-F013, M12-F014, M12-F015, M12-F016 | 4 | 0 | 0 | 12 | Core | FakeMessageBus + worker/AI/nested-scan/race fixtures + in-memory repositories
I-WP15 | Kiên | M14 | Security & Business Audit Capture | M14-F001, M14-F002, M14-F003, M14-F011 | 4 | 0 | 0 | 12 | Core | InMemoryAuditPort + mock admin/security events + correlation fixtures
I-WP16 | Kiên | M14 | Cross-Pipeline Correlation & Failure Trace | M14-F008, M14-F009 | 1 | 1 | 0 | 5 | Core | InMemoryAuditPort + mock admin/security events + correlation fixtures
I-WP17 | Kiên | M14 | Audit Query, Operations UI & Investigation | M14-F004, M14-F005, M14-F006, M14-F007, M14-F010 | 0 | 3 | 2 | 8 | Core | InMemoryAuditPort + mock admin/security events + correlation fixtures
T-WP01 | Thắng | M03 | Vietnamese Text Normalization & Evasion Handling | M03-F001, M03-F002, M03-F003, M03-F004, M03-F005, M03-F006, M03-F007 | 3 | 2 | 2 | 15 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP02 | Thắng | M03 | Async Text Scan, Scam Patterns & User Result UX | M03-F008, M03-F009, M03-F010, M03-F011, M03-F012, M03-F013, M03-F014, M03-F015 | 4 | 2 | 2 | 18 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP03 | Thắng | M03 | Entity Extraction from Text | M03-F016, M03-F017, M03-F018, M03-F019, M03-F020, M03-F021, M03-F022, M03-F023 | 5 | 2 | 1 | 20 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP04 | Thắng | M03 | Scam Taxonomy & User-facing Classification | M03-F024, M03-F025, M03-F026, M03-F027, M03-F028, M03-F029, M03-F030 | 1 | 3 | 3 | 12 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP05 | Thắng | M03 | Keyword Dictionary Administration | M03-F031, M03-F032, M03-F033, M03-F034, M03-F035, M03-F036, M03-F037 | 1 | 3 | 3 | 12 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP06 | Thắng | M03 | Multi-turn Conversation Analysis | M03-F038, M03-F039, M03-F040, M03-F041, M03-F042, M03-F043 | 0 | 3 | 3 | 9 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP07 | Thắng | M03 | Text Input Privacy & Worker Contract | M03-F044, M03-F045, M03-F046, M03-F047, M03-F048 | 4 | 1 | 0 | 14 | Core | FakeMessageBus + text/AI/derived-indicator fixtures + MockRiskEvaluationPort
T-WP08 | Thắng | M05 | QR/VietQR Decode, Classification & Nested Routing | M05-F001, M05-F002, M05-F003, M05-F004, M05-F005, M05-F006, M05-F009, M05-F010 | 7 | 1 | 0 | 23 | Core | QR fixtures + fake scan-platform/child-scan adapter; SSRF handled by M02 contract
T-WP09 | Thắng | M05 | Advanced QR Safety Checks | M05-F007, M05-F008 | 0 | 0 | 2 | 2 | Core | QR fixtures + fake scan-platform/child-scan adapter; SSRF handled by M02 contract
T-WP10 | Thắng | M06 | History Query, Access Control & Pagination | M06-F003, M06-F004, M06-F005, M06-F006 | 3 | 1 | 0 | 11 | Core | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
T-WP11 | Thắng | M06 | History Retention & User Management | M06-F001, M06-F002, M06-F007, M06-F008, M06-F009, M06-F010 | 1 | 3 | 2 | 11 | Core | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
T-WP12 | Thắng | M06 | RiskResult Contract & Presentation Components | M06-F011, M06-F012, M06-F013, M06-F014, M06-F020 | 3 | 2 | 0 | 13 | Core | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
T-WP13 | Thắng | M06 | Result Sharing & External Consumption | M06-F015, M06-F017, M06-F018 | 0 | 1 | 2 | 4 | Core | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
T-WP14 | Thắng | M06 | Async Export & Admin Reporting | M06-F016, M06-F019, M06-F021 | 0 | 2 | 1 | 5 | Core | RiskResult/history fixtures + mock object storage/export event + MockNotificationPort
T-WP15 | Thắng | M11 | AI Task/Result Contract & Worker Core | M11-F001, M11-F002, M11-F003, M11-F004, M11-F005, M11-F006, M11-F017, M11-F018 | 5 | 3 | 0 | 21 | Core | FakeMessageBus + ai request/result fixtures + mock provider adapters
T-WP16 | Thắng | M11 | AI Provider Resolver & Adapter Registry | M11-F009, M11-F019, M11-F020 | 1 | 1 | 1 | 6 | Core | FakeMessageBus + ai request/result fixtures + mock provider adapters
T-WP17 | Thắng | M11 | AI Safety, Prompt/Output Guardrails & Cache Options | M11-F007, M11-F008 | 0 | 0 | 2 | 2 | Core | FakeMessageBus + ai request/result fixtures + mock provider adapters
T-WP18 | Thắng | M11 | AI Evaluation Dataset, Metrics & Calibration | M11-F010, M11-F011, M11-F012, M11-F013, M11-F014, M11-F015, M11-F016 | 1 | 3 | 3 | 12 | Core | FakeMessageBus + ai request/result fixtures + mock provider adapters
H-FWP01 | Hùng | FUTURE | Future Entitlements, Plans & Subscription Boundary | FUTURE-F025, FUTURE-F026, FUTURE-F027, FUTURE-F028 | 0 | 0 | 4 | 4 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
H-FWP02 | Hùng | FUTURE | Future Usage, Credit Ledger & API Credentials | FUTURE-F029, FUTURE-F030, FUTURE-F031, FUTURE-F032, FUTURE-F033 | 0 | 0 | 5 | 5 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
K-FWP01 | Khải | FUTURE | Browser Extension Protection Surface | FUTURE-F001, FUTURE-F002, FUTURE-F003, FUTURE-F004, FUTURE-F005, FUTURE-F006 | 0 | 0 | 6 | 6 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
K-FWP02 | Khải | FUTURE | Community Contribution Gamification | FUTURE-F021, FUTURE-F022, FUTURE-F023 | 0 | 0 | 3 | 3 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
I-FWP01 | Kiên | FUTURE | Knowledge Library & Editorial Workflow | FUTURE-F007, FUTURE-F008, FUTURE-F009, FUTURE-F010, FUTURE-F011, FUTURE-F012 | 0 | 0 | 6 | 6 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
I-FWP02 | Kiên | FUTURE | Anti-Scam Quiz & Learning Evaluation | FUTURE-F019, FUTURE-F020 | 0 | 0 | 2 | 2 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
T-FWP01 | Thắng | FUTURE | Scam Q&A Assistant | FUTURE-F013, FUTURE-F014, FUTURE-F015, FUTURE-F016, FUTURE-F017, FUTURE-F018 | 0 | 0 | 6 | 6 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted
T-FWP02 | Thắng | FUTURE | Social Sharing for Learning/Engagement | FUTURE-F024 | 0 | 0 | 1 | 1 | Future | Build against current public ports/fixtures; must not change MVP contracts until promoted

## Meetings & Reports
Cycle | T5 Progress | T7 Progress | T2 Summary | T3 Lecturer | Lecturer Cadence | Checklist
B0 | 2026-10-01 | 2026-10-03 | 2026-10-05 | 2026-10-06 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W01 | 2026-10-08 | 2026-10-10 | 2026-10-12 | 2026-10-13 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W02 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-10-20 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W03 | 2026-10-22 | 2026-10-24 | 2026-10-26 | 2026-10-27 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W04 | 2026-10-29 | 2026-10-31 | 2026-11-02 | 2026-11-03 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W05 | 2026-11-05 | 2026-11-07 | 2026-11-09 | 2026-11-10 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W06 | 2026-11-12 | 2026-11-14 | 2026-11-16 | 2026-11-17 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W07 | 2026-11-19 | 2026-11-21 | 2026-11-23 | 2026-11-24 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W08 | 2026-11-26 | 2026-11-28 | 2026-11-30 | 2026-12-01 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W09 | 2026-12-03 | 2026-12-05 | 2026-12-07 | 2026-12-08 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W10 | 2026-12-10 | 2026-12-12 | 2026-12-14 | 2026-12-15 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W11 | 2026-12-17 | 2026-12-19 | 2026-12-21 | 2026-12-22 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W12 | 2026-12-24 | 2026-12-26 | 2026-12-28 | 2026-12-29 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W13 | 2026-12-31 | 2027-01-02 | 2027-01-04 | 2027-01-05 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W14 | 2027-01-07 | 2027-01-09 | 2027-01-11 | 2027-01-12 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W15 | 2027-01-14 | 2027-01-16 | 2027-01-18 | 2027-01-19 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W16 | 2027-01-21 | 2027-01-23 | 2027-01-25 | 2027-01-26 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W17 | 2027-01-28 | 2027-01-30 | 2027-02-01 | 2027-02-02 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W18 | 2027-02-04 | 2027-02-06 | 2027-02-08 | 2027-02-09 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W19 | 2027-02-11 | 2027-02-13 | 2027-02-15 | 2027-02-16 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W20 | 2027-02-18 | 2027-02-20 | 2027-02-22 | 2027-02-23 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W21 | 2027-02-25 | 2027-02-27 | 2027-03-01 | 2027-03-02 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W22 | 2027-03-04 | 2027-03-06 | 2027-03-08 | 2027-03-09 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W23 | 2027-03-11 | 2027-03-13 | 2027-03-15 | 2027-03-16 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W24 | 2027-03-18 | 2027-03-20 | 2027-03-22 | 2027-03-23 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W25 | 2027-03-25 | 2027-03-27 | 2027-03-29 | 2027-03-30 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W26 | 2027-04-01 | 2027-04-03 | 2027-04-05 | 2027-04-06 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W27 | 2027-04-08 | 2027-04-10 | 2027-04-12 | 2027-04-13 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W28 | 2027-04-15 | 2027-04-17 | 2027-04-19 | 2027-04-20 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W29 | 2027-04-22 | 2027-04-24 | 2027-04-26 | 2027-04-27 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W30 | 2027-04-29 | 2027-05-01 | 2027-05-03 | 2027-05-04 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W31 | 2027-05-06 | 2027-05-08 | 2027-05-10 | 2027-05-11 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W32 | 2027-05-13 | 2027-05-15 | 2027-05-17 | 2027-05-18 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W33 | 2027-05-20 | 2027-05-22 | 2027-05-24 | 2027-05-25 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W34 | 2027-05-27 | 2027-05-29 | 2027-05-31 | 2027-06-01 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W35 | 2027-06-03 | 2027-06-05 | 2027-06-07 | 2027-06-08 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W36 | 2027-06-10 | 2027-06-12 | 2027-06-14 | 2027-06-15 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W37 | 2027-06-17 | 2027-06-19 | 2027-06-21 | 2027-06-22 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W38 | 2027-06-24 | 2027-06-26 | 2027-06-28 | 2027-06-29 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W39 | 2027-07-01 | 2027-07-03 | 2027-07-05 | 2027-07-06 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W40 | 2027-07-08 | 2027-07-10 | 2027-07-12 | 2027-07-13 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W41 | 2027-07-15 | 2027-07-17 | 2027-07-19 | 2027-07-20 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W42 | 2027-07-22 | 2027-07-24 | 2027-07-26 | 2027-07-27 | Có | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV
W43 | 2027-07-29 | 2027-07-31 | 2027-08-02 | 2027-08-03 | Tuỳ chọn | T5: unblock/contract · T7: demo/review · T2: tick tracker + template report · T3: báo GV